## Sheet1
|  |  | Schematics Update | PCB Update
1 | Terminal blocks footprint needs to be changed 200 mil apart | sch, pcb | Done
2 | LCD connector too far left | pcb
3 | Knobs too far out holes are too close to the edge | pcb
4 | floating track on bottom layer around voltage input | pcb
5 | Polarity indicators on PCB blocks | pcb
6 | Q1(LCD on/off switch) is connected wrong | sch, pcb | Done
7 | Opamps VEE and LM334gnd pin requires a negative voltage | sch, pcb | Done
8 | seramic cap use in cout | sch, pcb | Done
9 | feedback loop for vset is wrong | sch, pcb | Done
10 | sdd 1N4148 from out pit to set pin | sch, pcb | Done
11 | add holes to PCB | pcb
12 | remove INA219 | sch, pcb | Done